## Sheet1
Sequential plan for preservation of St Dionysius, Ayton
Sequence | Item | Who | Cost | VAT | cost inc VAT | Status | 2022 | 2023 | 2024 | 2025 | 2026
1 | Survey of ruin by conservation architect | Adams Napier Partnership Ltd | 1950 | 390 | 2340 | complete
2 | environmental study | The Wildlife Partnership | 703.6 | 0 | 703.6 | complete
3 | ivy cutting to head height | volunteers | 0 | 0 | 0 | complete
4 | revised environmental study prior to ivy cutting | The Wildlife Partnership | 703.6 | 0 | 703.6 | complete
5 | removal of all ivy canopy (no stonework disturbance) | Alan Hogarth* | 20000 | 0 | 20000
6 | detailed assessment of building to determine order of work | Archaeology Scotland
7 | Stonework to Fordyce aisle | 1st phase | 47855 | 9571 | 57426
7.1 | workshops for interpretation of building by specialists
7.2 | evaluation of works by Archaeology Scotland
7.3 | advertising notices and leaflets
7.4 | open days and tours |  |  |  |  | 2 No to date of 5
7.5 | information board and leaflets
7.6 | time lapse video and history video |  |  |  |  | ongoing
7.7 | standard to meet requirement of Fallago Environment Fund Management Group
7.8 | develop partnership with Young Archaeologist Club, Local Youth Groups
7.9 | articles with local newspaper
7.1 | maintain repairs for 10 years after completion
7.11 | engage conservation architect |  |  |  |  | part time?
7.12 | comply with general and specific conditions of funders
7.13 | attainment course of Archaeology Scotland
7.14 | comply with publicity requirements of funders
7.15 | regular project reports to be issued
7.16 | maintain contacts with representatives of funders - mw suggestion
8 | Stonework to Nave-(west wall (1) , north wall west (2), south wall central (10), south wall west (11) | 2nd phase | 50714 | 10142.8 | 60856.8
9 | Stonework to Nave-(north wall east (7), east wall (8) ) plus south wall east (9) | 3rd phase | 42597 | 8519.4 | 51116.4
10 | Stonework to Northern-(west wall (3), north wall (4a and b) and east wall (6) | 4th phase | 33168 | 6633.6 | 39801.6
11 | Stonework to Northern-bell tower (5a,5b,5c) | 5th phase | 7712 | 1542.4 | 9254.4
12 | Stonework to Northern-burial aisle (Skene) (16a and 16b) | 6th phase | 6877 | 1375.4 | 8252.4
13 | Stonework to Northern -western burial aisle (Dickson) (15a and 15b) | 7th phase | 6785 | 1357 | 8142
14 | Stonework to South - eastern burial aisle (Cameron) (17) | 8th phase | 1867 | 373.4 | 2240.4
15 | Stonework to North Aisle (store) | 9th phase | 21859 | 4371.8 | 26230.8
16 | other costs
| temporary shoring |  | 2500 | 500 | 3000
| ground preparation |  | 3000 | 600 | 3600
| laboratory analysis |  | 2500 | 500 | 3000
| soft capping wallheads |  | 6000 | 1200 | 7200
|  | Totals | 256791.2 | 47076.8 | 303868
Reference numbers relate to Adams Napier report
* ivy removal estimate needs clarification